## Sheet1
Sprint Details | Tasks | Abhishek
Sprint - 1 | What tasks did I work on/ complete? | Requirement Analysis, Researching on Best Technologies for the requirement, Knowledge Transfer and Architectre Diagram
| What am I planning to work on next? | Understand the application flow, database design
| What blockers I have? | Have to learn about React from Scratch
Sprint - 2 | What tasks did I work on/ complete? | Class Diagram, Database Design Schema, Application flow and System Design
| What am I planning to work on next? | Learning react and Wireframes
| What blockers I have? | Have to learn about Integrations and data flow capture
Sprint - 3 | What tasks did I work on/ complete? | Learned React JSX, Components and Interaction. Completed wireframes for Booking
| What am I planning to work on next? | Learn more about React and develop logics for Booking
| What blockers I have? | Understaning react functionalities and props
Sprint - 4 | What tasks did I work on/ complete? | Learned React Lifecycle, Hooks, States. Developed logics to use rewards for payment
| What am I planning to work on next? | Work on implementing Booking page
| What blockers I have? | Interactions within the setup
Sprint - 5 | What tasks did I work on/ complete? | Finished Booking Page to retrieve Flight details, reward point details. And Booking Frontend to retrieve rewards logic
| What am I planning to work on next? | Work on Purchase seats and left work of Booking page
| What blockers I have? | Logics of core features
Sprint - 6 | What tasks did I work on/ complete? | Completed frontend for Purchase Seats. And frontend for Booking page to add Traveler Details
| What am I planning to work on next? | Minor updations and revising things
| What blockers I have? | Working with APIs and logics of backened DBs
Sprint - 7 | What tasks did I work on/ complete? | Worked on minor code changes and integration. Wrapped up creating the Architecture Diagram, Class Diagram, Task sheet, Burndown charts and Project Board
| What am I planning to work on next? | Cloud Implementation and Testing
| What blockers I have? | Integratio and data flow
Sprint - 8 | What tasks did I work on/ complete? | Install dependencies on Cloud, setup the EC2 Cluster and Auto scaling
| What am I planning to work on next? | Adding load balancers and CDNs
| What blockers I have? | N/A