## Sprint-1
Week #1 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
Requirement Analysis, Researching on Best Technologies for the requirement and Knowledge Transfer | Researching Technologies | All | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 0
| Architecture Diagram | All | 5 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Requirement Analysis | All | 7 | 6 | 5 | 5 | 4 | 2 | 1 | 0
| Learning and KT of React JS, Node JS | All | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 0
| Learning and KT of Mongo DB | All | 4 | 4 | 3 | 3 | 2 | 2 | 1 | 0
| Learning and KT of Python Flask | All | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 24 | 23 | 17 | 13 | 8 | 0
Team:
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-2
2021-10-14 |  |  |  | Week #2 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20
28
Application Flow and Database Design | Class Diagram | All | 5 | 8 | 5 | 4 | 2 | 0 | 0 | 0
| Design Database Schema | All | 5 | 8 | 6 | 6 | 5 | 3 | 1 | 0
| Application flow | All | 7 | 8 | 8 | 6 | 6 | 4 | 2 | 0
| System Design | All | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 1
| Project Set up (Node, React, JS) | All | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Backend Project Setup (Python, Flask, Mongo DB) | Nidhi | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 23 | 20 | 16 | 10 | 5 | 2
Team:
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-3
Week #3 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27
28
Database Implementation, Wireframes and APIs | Created Mongo DBs for Search Flights, User Details | Sai | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 0
| Created Mongo DBs for User Details | Sai | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0
| User Model, API for Signup, Login, User Details | Nidhi | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0
| Error Handling, JWT Authentication | Nidhi | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Wireframes for Home, Login, SignUp | Sameer | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
| Wireframes for Search Flights, Admin | Sameer | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0
| Learning React JSX, Components and Interaction | Abhishek | 6 | 6 | 5 | 4 | 2 | 1 | 0 | 0
| Wireframes for Booking | Abhishek | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  |  | 28 | 28 | 25 | 21 | 15 | 10 | 2 | 0
Team:
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-4
Week #4 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03
28
Development - Wireframes, Frontend and API | Frontend for Home, LogIn, SignUp | Sameer | 5 | 5 | 4 | 3 | 2 | 2 | 0 | 0
| Wireframe for Landing, Search flights, Bookings | Sameer | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Models and API for AirCraft, Add and Get Airport | Nidhi | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Models and API Add Flight, Search Flights | Nidhi | 4.5 | 4.5 | 3 | 2 | 1 | 1 | 1 | 0
| Mock data for Aircraft, Airport | Nidhi | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Learning React Lifecycle, Hooks, States | Abhishek | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 0
| Developed logics to use rewards for payment | Abhishek | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Worked on integrating flask APIs & MongoDB | Sai | 5 | 5 | 4 | 3 | 3 | 2 | 1 | 0
| MongoDB collections | Sai | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
|  |  | 28 | 28 | 22 | 16 | 11 | 9 | 4 | 0
Team:
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-5
Week #5 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10
28
Development - Frontend and API | Booking Page to retrieve Flight, Rewards Details | Abhishek | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0
| Booking Frontend and rewards logic | Abhishek | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1
| Worked on User Profile front end page | Sameer | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
| Frontend Change Reservation | Sai | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 1
| Frontend for Add, View | Sameer | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Frontend for Search Flights and Show Flights | Sameer | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 1
| API for Get all Flights, Update flight | Nidhi | 2.5 | 2.5 | 2 | 2 | 1 | 1 | 0 | 0
| Added Logger | Nidhi | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| API for Booking, Get bookings | Nidhi | 4 | 4 | 3 | 2 | 2 | 2 | 1 | 1
|  |  | 28 | 28 | 24 | 19 | 12 | 8 | 4 | 4
Team:
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-6
Week #6 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17
28
Development - Frontend and API | Created API for Cancel, Change Booking/Reservation | Nidhi | 4 | 4 | 4 | 2 | 2 | 1 | 0 | 0
| APIs for Purchase Seat, Get Available Seats | Nidhi | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0
| Frontend for My bookings (customer), My profile (customer) | Sameer | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Frontend for cancelling Admin and Customer | Sameer | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
| Created Mongo DBs for Booking Details | Sai | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0
| Merging DB schemas and updating collections | Sai | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
| Frontend for Purchase Seats | Abhishek | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
| Frontend for Booking page to add Traveler Details | Abhishek | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0
|  |  | 28 | 28 | 27 | 20 | 14 | 7 | 2 | 0
Team: |  | Total
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-7
Week #7 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24
28
Minor Code Changes + Integration | Minor Updations, Modifications & Integration | All | 7 | 7 | 6 | 5 | 4 | 3 | 2 | 0
| Minor Updations, Modifications & Integration | All | 7 | 7 | 5 | 4 | 3 | 3 | 2 | 1
| Minor Updations, Modifications & Integration | All | 7 | 7 | 6 | 6 | 4 | 3 | 2 | 0
| Minor Updations, Modifications & Integration | All | 7 | 7 | 5 | 3 | 2 | 1 | 0 | 0
|  |  | 28 | 28 | 22 | 18 | 13 | 10 | 6 | 1
Team: |  | Total
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-8
Week #7 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01
28
Integration Errors Resolving + Deployment + Testing + Remaining Work | Deployment | All | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| Testing | All | 7 | 7 | 5 | 4 | 4 | 3 | 1 | 0
| Resolving Integration Errors | All | 7 | 7 | 6 | 2 | 2 | 1 | 0 | 0
| Wrapping up the work | All | 7 | 7 | 6 | 5 | 4 | 3 | 2 | 1
|  |  | 28 | 28 | 23 | 15 | 13 | 9 | 4 | 1
Team: |  | Total
Sai Kapedakar | 7 hours / Week
Abhishek Reddy | 7 hours / Week
Nidhi Tholar | 7 hours / Week
Sameer Joshi | 7 hours / Week
Total Available Hours During Sprint: | 28

## Retrospective-Sprint-Sheet
Retrospective Report for Sprint - 1
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Technology Requirements | We discussed on different technologies and challenges associated with it starting from MongoDB, React, Flask, JS, Python and more | It took a while to settle down on tool we should implement becasue everyone wants to go with what they know | We were able to finalize on tech stack depending on different factors such as effectivenessm, easy of doing and time schedules
2 | Knowledge Transfer | Helped each other to make understand different tools and tech stacks they are experienced with | Pretty much this did go well | As we decided on tools and tech stack, we thought about proceeding further
3 | User Requirements Analysis | Thoroughly went through user requirements and components that need to be implemented | We were unable to understand a few things on how exactly we should implement as all of us have different ways to approach a problem | We split up the task and finalized to go with simple but effective solutions
Retrospective Report for Sprint - 2
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Class Diagram | Understood different componenets interactions and designed the class Diagram | Again it took a while to figure out which would be a critical component and how would the data pass to other components | For few componenets like Flight Search we still need enough requirements to proceed further
2 | Design Database Schema | All of us almost finalized the schema of DB and what should be implemented | Been complex at times to figure out the exact schema | Have to do more research and comeup with better solutions
3 | Application flow and System Design | Worked on this task for a lot of time, as they are many complex components involved | Couldn't figure out on a few components flow and inetaraction | How to setup the flow for other components like purchase seats
Retrospective Report for Sprint - 3
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Updating DB Schema and Implementation | Resolved initial conflicts and worked on creating schemas plus implemented a couple of DBs. And, merged schemas to remain consistent | Had to keep up with the changes and suggestions popping up with more analysis. Would've worked a bit more on initial gathering stage | Have to decide on more parameters
2 | Wireframes | Designed wireframes for a considerable no.of pages | Considerably good but had to work with placements for better viewing | Where to implement components for better usability
3 | Setup and APIs | Setup the backend depenencies, JWT Authentication, Error Handling, Loggers | Took a lot of time to understand resolve conflicts assocated with login and request handling. Decided to pass it for sometime | How to handle conflicting requests and passing JWT tokens
4 | Learning and test practice | Spent a good time on learning React from scrach and worked on creating test and project modules | Been tough as had to learn from Scratch. Couldn't understand certain functionalites but tried to resolve | How do components interact specailly with inconsistent parameters
Retrospective Report for Sprint - 4
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Worked on a lot of different frontend pages like Home, Login and signups. Almost of the work is completed | Had to solve some data passing issues with authentications | Have to work on learning more about authentications
2 | APIs | Build APIs for crucial functions like Search, Update and Bokoing flight | Collaborating and understanding different input and out paramets has been complex | How to Fix and setup the parameters
3 | Logics and Test Integrations | Worked on flow logics to make consistent without breakdowns and tested a few integrations | Few of them didn't work as expected making one doesn't interact with the another | Building more reliable interactions
Retrospective Report for Sprint - 5
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Started working on major Booking page, User Profile, Change Reservations, add and view, search flights | Lot of complexities involved in writing the logics of core functionalites like booking and search flights | Learned more about the requirements and have to study about algorithms involved to implement components
2 | APIs | Also completed working on APIs to get all flights, search and show flights, booking and get booking. Added logger too | Working back anf forth with DB and Frontend has been complex and didn't go well at times | How to seamlessly integrate and pass the data required to and forth between backend Databases and Frontend
Retrospective Report for Sprint - 6
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Completed the previous challenges and completed working on Frontend for My Bookings, My Profile for customer and frontend for cancelling Admin and Customer | Couldn't implement certain functionalities due to time constraints. Postponed some works towards the next sprint | Have to manage time well and splitup the prorities balancing the functionality and UI
2 | APIs | Finished working on Cancel, Change Booking, Purchase seats and get available seats APIs | Can't get the idea to use better techniques to build a few functions inside individual API | Should learn more multiple and complex endpoints
3 | Databases | Created DBs for Booking and resolved the issues of merge conflicts in DBs along with updating collections | Defining and following schemas with error formating has been challenging | Needs to learn more about implementing quickly
Retrospective Report for Sprint - 7
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Minor Code Changes | Most of the core functionalities implementation has been successfully implemented. Did minor code changes to decrease dependencies and support data flow | One of the ddificult challenges has been to keep the session and data flow. Though the code changes are minor, selective functions and lines were hard to find and change | Plan things accordingly and test selected components at before hand. Work more on collaboration and fixing the requirement parameters
2 | Integration | Successfully completed integrating almost all the components locally | Certain compoenents are inconsistent to integrate | Plan things accordingly and test selected compoenents at before hand. Work more on collaboration and fixing the requirement parameters
Retrospective Report for Sprint - 8
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Resolving Minor Integration Errors | Completely done with integration and resolved all the issues | Almost all the things did go well as we've been prepared | Things went well as expected
2 | Deployment | Successfully deployed on EC2 Autoscale cluster and had it running flawlessly | Faced a few security, identity access and dependencies installment issue. Minor to resolve them at hand | More about configuring secuirty policies
3 | Testing | Testing mutliple times with different outputs and system conditions | We took care of this aspect so nothing much | Nothing as such
4 | Retrospection | Revised everything from the start, how we carried on, initial agends and final achievements, challenges and pain points, what to work on and how to improve and more. | There will always be room for improvements. Learning from those challenges and moving forwardg is the crucial thing. | Confidently we can say we achieved what we expected at the rate of 95%.