## Sheet1
Sprint Details | Tasks | SAI
Sprint - 1 | What tasks did I work on/ complete? | Requirement Analysis, Researching on Best Technologies for the requirement, Knowledge Transfer and Architectre Diagram
| What am I planning to work on next? | Understand the application flow, database design and Github working.
| What blockers I have? | Installing technologies on WSL
Sprint - 2 | What tasks did I work on/ complete? | Class Diagram, Database Design Schema, Application flow and System Design
| What am I planning to work on next? | Setting up MongoDB on Cloud, creating Database skeleton, Understanding how frontend works
| What blockers I have? | Learning React, javascript and other frontend technologies
Sprint - 3 | What tasks did I work on/ complete? | Installed all the required software on my system, Developed DB on MongoDB atlas, created all the required collections, Created Mock data for User details page
| What am I planning to work on next? | Learn more about React and develop frontend page for User profile
| What blockers I have? | Understaning connection between Frontend, MongoDB Atlas and backend APIs
Sprint - 4 | What tasks did I work on/ complete? | Developed User profile frontend page, Understood how connection string on Atlas works
| What am I planning to work on next? | Understanding the working of change reservation and develop a code to implement it, Mock data for entire system
| What blockers I have? | Not clear functionality
Sprint - 5 | What tasks did I work on/ complete? | Integrating and testing User profile along with MongoDB on cloud
| What am I planning to work on next? | Develop change reservation and deploying the project on AWS cloud EC2 instance
| What blockers I have? | Understanding how to deploy, what is Ec2 and Auto scaling
Sprint - 6 | What tasks did I work on/ complete? | Established EC2 instance and remote desktop client
| What am I planning to work on next? | Auto scaling and deploying project to AWS
| What blockers I have? | Understanding AWS deployments
Sprint - 7 | What tasks did I work on/ complete? | Created mock data according to flow of the project, integrated frontend, backend and database
| What am I planning to work on next? | Deploying using CodeDeploy or Putty to remote desktop client
| What blockers I have? | Working project as one, deploying on windows system
Sprint - 8 | What tasks did I work on/ complete? | Deploying working project on cloud and accessing it through public url
| What am I planning to work on next? | Accessing public url while optimizing CPU performance
| What blockers I have? | N/A