## Retrospective-Sprint-Sheet
Retrospective Report for Sprint - 1
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Technology Requirements | We discussed on different technologies and challenges associated with it starting from MongoDB, React, Flask, JS, Python and more | It took a while to settle down on tool we should implement becasue everyone wants to go with what they know | We were able to finalize on tech stack depending on different factors such as effectivenessm, easy of doing and time schedules
2 | Knowledge Transfer | Helped each other to make understand different tools and tech stacks they are experienced with | Pretty much this did go well | As we decided on tools and tech stack, we thought about proceeding further
3 | User Requirements Analysis | Thoroughly went through user requirements and components that need to be implemented | We were unable to understand a few things on how exactly we should implement as all of us have different ways to approach a problem | We split up the task and finalized to go with simple but effective solutions
Retrospective Report for Sprint - 2
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Class Diagram | Understood different componenets interactions and designed the class Diagram | Again it took a while to figure out which would be a critical component and how would the data pass to other components | For few componenets like Flight Search we still need enough requirements to proceed further
2 | Design Database Schema | All of us almost finalized the schema of DB and what should be implemented | Been complex at times to figure out the exact schema | Have to do more research and comeup with better solutions
3 | Application flow and System Design | Worked on this task for a lot of time, as they are many complex components involved | Couldn't figure out on a few components flow and inetaraction | How to setup the flow for other components like purchase seats
Retrospective Report for Sprint - 3
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Updating DB Schema and Implementation | Resolved initial conflicts and worked on creating schemas plus implemented a couple of DBs. And, merged schemas to remain consistent | Had to keep up with the changes and suggestions popping up with more analysis. Would've worked a bit more on initial gathering stage | Have to decide on more parameters
2 | Wireframes | Designed wireframes for a considerable no.of pages | Considerably good but had to work with placements for better viewing | Where to implement components for better usability
3 | Setup and APIs | Setup the backend depenencies, JWT Authentication, Error Handling, Loggers | Took a lot of time to understand resolve conflicts assocated with login and request handling. Decided to pass it for sometime | How to handle conflicting requests and passing JWT tokens
4 | Learning and test practice | Spent a good time on learning React from scrach and worked on creating test and project modules | Been tough as had to learn from Scratch. Couldn't understand certain functionalites but tried to resolve | How do components interact specailly with inconsistent parameters
Retrospective Report for Sprint - 4
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Worked on a lot of different frontend pages like Home, Login and signups. Almost of the work is completed | Had to solve some data passing issues with authentications | Have to work on learning more about authentications
2 | APIs | Build APIs for crucial functions like Search, Update and Bokoing flight | Collaborating and understanding different input and out paramets has been complex | How to Fix and setup the parameters
3 | Logics and Test Integrations | Worked on flow logics to make consistent without breakdowns and tested a few integrations | Few of them didn't work as expected making one doesn't interact with the another | Building more reliable interactions
Retrospective Report for Sprint - 5
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Started working on major Booking page, User Profile, Change Reservations, add and view, search flights | Lot of complexities involved in writing the logics of core functionalites like booking and search flights | Learned more about the requirements and have to study about algorithms involved to implement components
2 | APIs | Also completed working on APIs to get all flights, search and show flights, booking and get booking. Added logger too | Working back anf forth with DB and Frontend has been complex and didn't go well at times | How to seamlessly integrate and pass the data required to and forth between backend Databases and Frontend
Retrospective Report for Sprint - 6
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Completed the previous challenges and completed working on Frontend for My Bookings, My Profile for customer and frontend for cancelling Admin and Customer | Couldn't implement certain functionalities due to time constraints. Postponed some works towards the next sprint | Have to manage time well and splitup the prorities balancing the functionality and UI
2 | APIs | Finished working on Cancel, Change Booking, Purchase seats and get available seats APIs | Can't get the idea to use better techniques to build a few functions inside individual API | Should learn more multiple and complex endpoints
3 | Databases | Created DBs for Booking and resolved the issues of merge conflicts in DBs along with updating collections | Defining and following schemas with error formating has been challenging | Needs to learn more about implementing quickly
Retrospective Report for Sprint - 7
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Minor Code Changes | Most of the core functionalities implementation has been successfully implemented. Did minor code changes to decrease dependencies and support data flow | One of the ddificult challenges has been to keep the session and data flow. Though the code changes are minor, selective functions and lines were hard to find and change | Plan things accordingly and test selected components at before hand. Work more on collaboration and fixing the requirement parameters
2 | Integration | Successfully completed integrating almost all the components locally | Certain compoenents are inconsistent to integrate | Plan things accordingly and test selected compoenents at before hand. Work more on collaboration and fixing the requirement parameters
Retrospective Report for Sprint - 8
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Resolving Minor Integration Errors | Completely done with integration and resolved all the issues | Almost all the things did go well as we've been prepared | Things went well as expected
2 | Deployment | Successfully deployed on EC2 Autoscale cluster and had it running flawlessly | Faced a few security, identity access and dependencies installment issue. Minor to resolve them at hand | More about configuring secuirty policies
3 | Testing | Testing mutliple times with different outputs and system conditions | We took care of this aspect so nothing much | Nothing as such
4 | Retrospection | Revised everything from the start, how we carried on, initial agends and final achievements, challenges and pain points, what to work on and how to improve and more. | There will always be room for improvements. Learning from those challenges and moving forwardg is the crucial thing. | Confidently we can say we achieved what we expected at the rate of 95%.